## Overview
AI-powered Chatbot System - Master PM Task Deliverables Summary
Tab Name | Task / Module | Key Focus & Deliverables | Core Metrics & Outputs
Tab 0: Overview | Executive Landing | Metadata, submission index, and project scope summary. | Master navigation hub for evaluators.
Tab 1: Task 1 | User Stories & Points | 10 Agile user stories across Knowledge Base, Prompts, Inbox, Widget, and Handoff. | 10 Stories ¦ 47 Story Points (Fibonacci scale).
Tab 2: Task 2 | UI Wireframes & Specs | UI component layout specs and ASCII wireframe maps for 3 core interfaces. | 10 UI Components across Admin Inbox, Knowledge Base, and Widget.
Tab 3: Task 3 | Project Timeline | Work Breakdown Structure (WBS), Gantt roadmap, and role responsibilities. | 800 Man-Hours ¦ 2 Months (8 Weeks) ¦ 5 Team Members.
Tab 4: Task 4 | Cost Estimation | CAPEX development labor cost calculation and OPEX running cost notes. | 600,000 Total Labor Cost + API/Hosting OPEX.
Tab 5: Task 5 | Competitor Analysis | Feature parity matrix (Tawk.to, Chatbase, Crisp) and proposed value-add features. | 4 Strategic Features (Sentiment Escalation, AI Copilot, etc.).

## Task1_UserStories
Task 1: User Stories
Total Story Points: 47 Points
Key Summary Breakdown
| Total Stories: | 10
| Modules Covered: | Knowledge Base & Scraping (3), AI Config (1), Chat Widget (1), Omnichannel Inbox (3), Agent Handoff (2).
Story Point Distribution:
2 Points: Simple UI filtering (US-07).
3 Points: Basic forms & metadata views (US-03, US-04, US-08).
5 Points: Multi-step client/server operations (US-01, US-05, US-09, US-10).
8 Points: Complex background pipelines & external integrations (US-02, US-06).
User Stories Table
Story ID | Epic (Module) | User Role | User Story | Acceptance Criteria | Priority | Story Points
US-01 | Knowledge Base | Admin | As an Admin, I want to upload CSV, PDF, TXT, and Markdown files, so that the chatbot can use custom internal documents to answer customer questions. | 1. Accepts .pdf, .csv, .txt, and .md formats up to 25MB. 2. Shows file upload progress bar and validation errors for corrupted files. 3. Automatically extracts raw text, converts it into Markdown, and indexes it into the vector database. | High | 5
US-02 | Knowledge Base | Admin | As an Admin, I want to enter a website URL in a "Train from Website" field, so that the AI can scrape the web pages and train on live web content. | 1. Admin inputs valid http/https URL and clicks "Train". 2. UI displays real-time crawling status ("Fetching...", "Extracting...", "Complete"). 3. Scraped text is converted to Markdown format and saved in the Trained Directory. 4. Error message is thrown if page is unreachable or behind a paywall. | High | 8
US-03 | Knowledge Base | Admin | As an Admin, I want to view, edit, search, and delete documents in a "Trained Directory", so that I can keep chatbot training material updated and accurate. | 1. Directory displays table listing file name, source type (File/URL), date added, and status. 2. Clicking a document opens a Markdown editor to modify text directly. 3. Deleting a record purges it from the vector index immediately. | Medium | 3
US-04 | AI Configuration | Admin | As an Admin, I want to configure system prompts, tone, and guardrails, so that the AI responds according to company guidelines and brand voice. | 1. Text area provided for system prompt input (max 2,000 characters). 2. Preset options available for tone (e.g., Professional, Friendly, Concise). 3. Admin can set default fallback responses when AI confidence is low. | High | 3
US-05 | Chat Widget | Customer | As a Website Visitor, I want to open a floating chat widget and ask questions, so that I get instant automated support based on company data. | 1. Floating bubble loads on site bottom-right without impacting page load speed. 2. Displays typing indicator while AI generates a response. 3. Retains session chat history during a single browsing session. | High | 5
US-06 | Omnichannel Inbox | Support Agent | As a Support Agent, I want to view all customer messages from Web, Facebook, Instagram, and WhatsApp in a single inbox, so that I don't have to switch between apps. | 1. Unified inbox lists incoming chats sorted by last active timestamp. 2. Clear icon badges indicate channel origin (Website, FB, IG, WhatsApp). 3. Real-time WebSockets push new incoming messages without manual page refresh. | High | 8
US-07 | Omnichannel Inbox | Support Agent | As a Support Agent, I want to filter the inbox by channel source, so that I can focus on specific communication channels when needed. | 1. Filter dropdown/tabs for "All", "Website", "Facebook", "Instagram", "WhatsApp". 2. Unread badge counts update dynamically per filter view. | Medium | 2
US-08 | Omnichannel Inbox | Support Agent | As a Support Agent, I want to view detailed customer profile metadata and full conversation history in the inbox side panel, so that I have full context before responding. | 1. Side panel displays contact name, email, phone number, and location (if captured). 2. Scrollable timeline showing previous interactions across all connected channels. | Medium | 3
US-09 | Agent Handoff | Support Agent | As a Support Agent, I want to manually switch a chat from "AI Mode" to "Human Mode", so that I can stop automated bot responses and take over the conversation directly. | 1. Prominent UI toggle switch showing current state ("AI Mode" vs "Human Mode"). 2. Toggling to "Human Mode" disables AI auto-reply and unlocks the agent text input box. 3. System posts a non-customer-facing system event log: "Agent [Name] joined the chat." | High | 5
US-10 | Agent Handoff | Admin | As an Admin, I want the system to automatically trigger a Human Handover if the AI cannot answer or if the user requests a human, so that customer frustration is minimized. | 1. Automatically flips toggle to "Human Mode" if AI confidence score drops below preset threshold. 2. Keywords like "talk to agent" or "human support" immediately trigger handover. 3. Sends an unread priority notification alert to online agents in the dashboard. | Medium | 5

## Task2_Wireframes
Task 2: Wireframes
Tool Used: Draw.io (Diagrams.net)
Key Summary Breakdown
| Total UI Components: | 10 core elements across 3 distinct screens
Wireframes Below
| Screens Modeled: | 1. Omnichannel Inbox & Dashboard: Features channel filters, real-time message viewport, user metadata sidebar, and live AI/Human mode toggle. 2. Knowledge Base Section: Drag-and-drop file uploader, URL crawler with status indicator, and Markdown document manager directory. 3. Customer Chat Widget: Website floating bubble with interactive states. |  | ⬇️
Design Guidelines:
1. Clean visual layout hierarchy using standard grid structures.
2. Explicit contrast between automated AI events and human agent interactions.
3. Direct structural compatibility with draw.io / Figma diagram exports.
Wireframe Specifications Table
Component ID | Screen Name | Layout Area | UI Element / Feature | Functional Description | Interaction & State Notes
WF-01 | Admin Dashboard | Left Navigation | Navigation Sidebar | Menu items: Inbox, Knowledge Base, AI Prompts, Analytics, Settings. | Active tab highlight. Collapsible for expanded workspace.
WF-02 | Admin Dashboard | Center Left | Chat Conversations Feed | Scrollable list of active threads showing user name, preview message, and timestamp. | Includes channel badge icons (Web, FB, IG, WhatsApp) and unread count badges.
WF-03 | Admin Dashboard | Top Header | Channel Filter Bar | Filter tabs/dropdown: All, Website, Facebook, Instagram, WhatsApp. | Updates thread feed dynamically upon selection.
WF-04 | Admin Dashboard | Center Panel | Real-Time Chat Viewport | Main messaging screen with scrollable history and message input box. | Shows system event notes (e.g., "Agent took over chat").
WF-05 | Admin Dashboard | Top Right Header | Mode Toggle Switch | Interactive toggle switch labeled "AI Mode" / "Human Mode". | Green badge = AI active. Amber badge = Human active. Disables/enables manual input field.
WF-06 | Admin Dashboard | Right Side Panel | Customer Metadata View | Displays user email, phone number, location, total visits, and channel source. | Scrollable timeline view showing previous interactions.
WF-07 | Knowledge Base | Top Section | Document Drag & Drop | Upload zone accepting PDF, CSV, TXT, and Markdown files (max 25MB). | Shows visual progress bar during processing and text extraction.
WF-08 | Knowledge Base | Middle Section | "Train from Website" Form | URL text input field with a prominent "Train / Crawl" CTA button. | Real-time status indicator text: "Fetching URL..." $\rightarrow$ "Extracting Data..." $\rightarrow$ "Complete".
WF-09 | Knowledge Base | Bottom Section | Trained Directory Table | Data table listing File Name, Source Type (File/URL), Date Added, and Actions. | Actions: View/Edit Markdown (opens modal editor) and Delete (purges from vector DB).
WF-10 | Chat Widget | Bottom-Right Floating | Widget Bubble / Expanded | Minimizable floating icon that opens into a $380\text{px} \times 600\text{px}$ chat window on the website. | Shows header with bot branding, real-time typing indicators, and session chat log.

## Task3_ProjectTimeline
Task 3: Project Timeline
| Key Summary Breakdown |  |  | Gantt Chart on right |  |  |  | Gantt Chart Table
|  |  |  | ➡️ |  |  | Phase Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
| Total Time: | 800 Man-Hours |  |  |  |  | Phase 1: Discovery & UI/UX | bar: Gantt Chart Table Week 1 to Gantt Chart Table Week 2
Phase 2: Core Backend & DB | bar: Gantt Chart Table Week 2 to Gantt Chart Table Week 4
| Total Effort: | 800 Man-Hours. |  |  |  |  | Phase 3: Frontend Build | bar: Gantt Chart Table Week 3 to Gantt Chart Table Week 5
| Project Duration: | 2 Months / 8 Weeks / 40 Business Days. |  |  |  |  | Phase 4: Omnichannel & AI | bar: Gantt Chart Table Week 5 to Gantt Chart Table Week 7
| Team Composition: | 5 Members (1 PM, 1 UI/UX, 1 Backend, 1 Frontend, 1 QA). |  |  |  |  | Phase 5: QA & Bug Fixing | bar: Gantt Chart Table Week 6 to Gantt Chart Table Week 8
Phase 6: Deployment & Launch | bar: Gantt Chart Table Week 8
Story Point Distribution:
2 Points: Simple UI filtering (US-07).
3 Points: Basic forms & metadata views (US-03, US-04, US-08).
5 Points: Multi-step client/server operations (US-01, US-05, US-09, US-10).
8 Points: Complex background pipelines & external integrations (US-02, US-06).
Team Structure Table
Role Title | Headcount | Allocated Time | Core Responsibilities | Key Deliverables
Project Manager (PM) | 1 | 2 Months (100%) | Project roadmap, sprint planning, client communication, risk management, and daily standups. | PRD, Sprint Backlog, Gantt Schedule, Delivery Reports.
UI/UX Designer | 1 | 1 Month (50% overall) | User flows, wireframes, component library, and high-fidelity Figma prototypes. | Dashboard Layouts, Chat Widget Specs, Interactive Prototypes.
Backend Developer | 1 | 2 Months (100%) | Vector DB setup, LLM API integration, web scraping pipeline, Meta/WhatsApp webhooks, DB design. | Database Schema, Web Crawler, Webhooks, REST/GraphQL APIs.
Frontend Developer | 1 | 2 Months (100%) | Admin dashboard UI (React/Next.js), chat widget script, real-time WebSockets, training page UI. | Responsive Admin Dashboard, Embedded Chat Widget.
QA Engineer | 1 | 1.5 Months (75% overall) | Test plan creation, API testing, end-to-end integration testing across channels, bug tracking. | Test Cases, Automation Scripts, Bug Reports, Release Sign-off.
Work Breakdown Structure Table
Phase # | Phase / Milestone Name | Key Activities & Tasks | Assigned Roles | Man-Hour Estimation | Duration (Days) | Target Schedule
Phase 1 | Discovery & UI/UX Design | Requirements freeze, architecture planning, Figma UI wireframes, chat widget layout design. | PM, UI/UX | 120 hrs | 15 Days | Weeks 1 – 3
Phase 2 | Core Architecture & Backend | Database schema setup, OpenAI API integration, Vector DB indexing, Web Scraper development. | Backend Dev, PM | 200 hrs | 20 Days | Weeks 2 – 5
Phase 3 | Frontend & Admin Dashboard | Dashboard layout build, Knowledge Base UI, Training Directory, Embeddable Chat Widget script. | Frontend Dev, UI/UX | 160 hrs | 20 Days | Weeks 3 – 6
Phase 4 | Omnichannel & AI Integration | Meta Webhooks (FB/IG), WhatsApp API sync, AI/Human Toggle logic, Real-time WebSocket messaging. | Backend, Frontend | 160 hrs | 15 Days | Weeks 5 – 7
Phase 5 | Testing, Bug Fixing & QA | Integration testing across channels, web scraper edge-case testing, load testing, bug resolution. | QA, All Devs | 120 hrs | 10 Days | Weeks 6 – 8
Phase 6 | Deployment & Handover | Production deployment, server setup, documentation completion, admin user training. | PM, Backend Dev | 40 hrs | 5 Days | Week 8
TOTAL | Full Development Lifecycle | End-to-End System Build | Entire Team | 800 hrs | 40 Days | 2 Months

## Task4_CostEstimation
Task 4: Cost Estimation
Project Duration: 2 Months (8 Weeks)
Key Summary Breakdown
| Total Labor Cost: | 600000
| Cost Basis: | Resource allocation percentages based on the Project timeline roadmap.
Justification:
PM, Backend, & Frontend: Full-time dedicated commitment across the entire 2-month lifecycle
UI/UX Designer: Equivalent to 1 full month concentrated heavily in Phase 1 & 2 for wireframes and design system setup.
5 Points: Multi-step client/server operations (US-01, US-05, US-09, US-10).
8 Points: Complex background pipelines & external integrations (US-02, US-06).
Cost Breakdown Table
Role Title | Monthly Rate | Project Duration | Resource Allocation (%) | Allocated Months | Total Cost Calculation | Total Line Cost
Project Manager (PM) | 60000 | 2 Months | 100% | 2 | 120000 | 120000
UI/UX Designer | 50000 | 2 Months | 50% | 1 | 50000 | 50000
Backend Developer | 100000 | 2 Months | 100% | 2 | 200000 | 200000
Frontend Developer | 70000 | 2 Months | 100% | 2 | 140000 | 140000
QA Engineer | 60000 | 2 Months | 75% | 1.5 | 90000 | 90000
TOTAL LABOR COST |  |  |  |  | Sum of all roles | 600000
Operational Expenditure (OPEX) Estimation
OPERATIONAL INFRASTRUCTURE ESTIMATION (OPEX - THIRD-PARTY SERVICES)
Note: Operational costs are ongoing usage-based expenses separate from initial development labor costs.
1. LLM API Usage (OpenAI / Anthropic): |  | Variable cost based on query volume (~$0.0015 / 1K tokens).
2. Vector Database Hosting (Pinecone / Qdrant): |  | ~$70–$100 / month for document embeddings storage.
3. Meta Business API (WhatsApp Messaging): |  | ~$70–$100 / month for document embeddings storage.
4. Cloud Infrastructure (AWS / GCP / Vercel): |  | ~$50–$100 / month for server hosting & WebSockets.

## Task5_CompetitorAnalysis
Task 5: Competitor Analysis
Key Summary Breakdown
| Competitors Evaluated: | Tawk.to, Chatbase, Crisp / Intercom
| Market Positioning: | Bridges the gap between raw AI chatbot builders (like Chatbase) and dedicated support inbox tools (like Tawk.to) by offering an all-in-one SMB solution.
| Competitive Edge: | Native multi-channel webhooks combined with Markdown-based live knowledge base training and real-time AI/Human toggling.
| Value-Add Focus: | Enhancements prioritize agent productivity (AI Copilot), customer retention (Sentiment Escalation), and knowledge freshness (Scheduled Re-Indexing).
Product Research & Competitor Analysis
Feature / Capability | Proposed System | Tawk.to | Chatbase / CustomGPT | Crisp / Intercom
Custom AI Document Training (PDF, CSV, MD) | Full Support | No Native Support | Full Support | Add-on / Limited
"Train from Website" Web Scraper | Full Support | No Native Support | Full Support | Basic URL Indexing
Omnichannel Inbox (FB, IG, WhatsApp, Web) | Full Support | Partial (Web/WhatsApp) | No Native live box | Full Support
Real-Time Human Agent Handoff / Toggle | Full Support | Full Support | Weak / Third-party only | Full Support
Markdown Knowledge Base Directory | Full Support | No | View Only | Internal KB
Target Pricing Tier | Mid-Market / SMB | Free / Low Cost | API Tiered | Enterprise Tier (High)
Proposed Value-Adding Features
Feature | Proposed Feature | Category | Description & User Value | Strategic Impact & ROI
VF-01 | Smart Sentiment Escalation | AI / Support Automation | Automatically detect negative customer sentiment, frustration keywords, or repetitive loops in real time and trigger automatic human agent handover. | Prevents customer churn and lowers drop-off rates during poor AI interactions.
VF-02 | AI Copilot for Human Agents | Agent Productivity | When in "Human Mode", provide reps with AI-suggested draft responses, quick knowledge base search, and auto-summaries of the chat history. | Drastically reduces Average Handle Time (AHT) and speeds up human response times.
VF-03 | Automated Scheduled Re-Indexing | Knowledge Base | Allow admins to set cron-scheduled crawls (e.g., weekly/monthly) on training URLs to auto-update Markdown data. | Eliminates manual re-training maintenance and ensures the AI never gives stale information.
VF-04 | Unanswered Query & Knowledge Gap Insights | Analytics | An analytics dashboard aggregating questions where the AI had low confidence scores or requested human handoff. | Provides admins with direct data on what missing content needs to be uploaded to the knowledge base.